AMLIQ

Competitive Gap Sprint Plan

Close every gap vs World-Check in 8 weeks

Engineer: Shachar Solomon (Solo)

Sprint Cadence: 2-week sprints (4 sprints total)

Timeline: April 14 – June 6, 2026

Objective: Close ALL 7 competitive gaps identified in AMLIQ vs World-Check analysis

Prepared: April 13, 2026

# Executive Summary

This plan sequences 7 competitive gaps into 4 two-week sprints, totaling 8 weeks of solo development. Each sprint delivers shippable value. By June 6, AMLIQ will match or beat World-Check on every dimension except raw data volume (which we counter with OpenSanctions partnership).

## Capacity Planning

| Sprint | Dates | Working Days | Available Days | Notes |
| --- | --- | --- | --- | --- |
| Sprint 49 | Apr 14–25 | 10 | 8 | 2 days buffer for unknowns |
| Sprint 50 | Apr 28–May 9 | 10 | 8 | 2 days buffer |
| Sprint 51 | May 12–23 | 10 | 8 | 2 days buffer |
| Sprint 52 | May 26–Jun 6 | 10 | 8 | 2 days buffer + final QA |

Planned at 80% capacity (8 of 10 days) to absorb interrupts, debugging, and unforeseen complexity.

## Gap Overview — All 7 Gaps Mapped to Sprints

| Gap | Severity | Sprint | Story Points | Definition of Done |
| --- | --- | --- | --- | --- |
| PEP Sub-Classification | HIGH | 49 | 8 pts | Domestic/Foreign/SOE/RCA PEP types in schema, ingestion, and screening |
| Audit Log Persistence | MEDIUM | 49 | 5 pts | Audit events persisted to PostgreSQL with 7-year retention policy |
| Country Risk Scoring | MEDIUM | 49 | 5 pts | Configurable per-tenant country risk index using CPI + Basel + FATF |
| UBO API + Enrichment | HIGH | 50 | 13 pts | Full CRUD API, OpenCorporates/GLEIF integration, screening pipeline |
| Vessel/Maritime Screening | MEDIUM | 51 | 8 pts | OFAC vessel parsing enabled, vessel screening page, entity type support |
| SOC 2 Type II Certification | HIGH | 51–52 | 8 pts | Auditor engaged, evidence collection, gap remediation complete |
| Data Depth Partnership | HIGH | 52 | 5 pts | OpenSanctions Premium contract signed, PEP + adverse media enrichment live |

# Sprint 49: PEP Intelligence + Compliance Foundation

April 14 – April 25, 2026  |  Capacity: 8 days  |  Load: 18 points (100%)

Sprint Goal: Achieve World-Check-grade PEP sub-classification and build compliance infrastructure for SOC 2 readiness.

### Goal 1: PEP Sub-Classification (8 pts) — P0

World-Check sub-classifies PEPs into domestic, foreign, international org, SOE, and RCA. AMLIQ has a 4-tier system but lacks these distinctions. This is the #1 gap enterprise buyers will probe.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Add PEP classification fields to Entity domain | 3h | D1 | internal/domain/entity.go, pep.go |
| 2 | Add IsDomestic, IsForeign, IsSOE, IsRCA fields | 2h | D1 | internal/domain/pep.go |
| 3 | Create PEP classifier service | 4h | D2 | internal/screening/pep_classifier.go (new) |
| 4 | Integrate classifier into OpenSanctions ingestion | 4h | D2-D3 | internal/ingestion/opensanctions_pep_tier.go |
| 5 | Classify SOE entities as PEP-level risk | 3h | D3 | internal/ingestion/wikidata_soe.go |
| 6 | Wire RCA relations into screening match cascade | 4h | D4 | internal/screening/graph.go, engine.go |
| 7 | Add PEP sub-type filter to Configuration page | 3h | D4 | web/src/pages/Configuration.tsx |
| 8 | Table-driven tests for all PEP classification paths | 4h | D5 | internal/screening/pep_classifier_test.go |
| 9 | Update PEPScreening page with sub-type badges | 2h | D5 | web/src/pages/PEPScreening.tsx |

### Goal 2: Audit Log Persistence (5 pts) — P0

Current audit logger is in-memory only. SOC 2 requires durable, tamper-evident audit trails with retention policies.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Create audit_events PostgreSQL table migration | 2h | D6 | migrations/031_audit_events.sql (new) |
| 2 | Implement persistent audit repository | 4h | D6 | internal/storage/pgx/audit_repo.go (new) |
| 3 | Replace in-memory logger with DB-backed logger | 3h | D7 | internal/security/audit_logger.go |
| 4 | Add 7-year retention policy + archival job | 2h | D7 | cmd/worker/audit_archive.go (new) |
| 5 | Add audit log query API endpoint | 3h | D7 | api/handler_audit.go |
| 6 | Table-driven tests for audit persistence | 2h | D8 | internal/security/audit_logger_test.go |

### Goal 3: Configurable Country Risk Scoring (5 pts) — P1

Current risk scoring is a hardcoded 15-country map. Enterprise customers need configurable, data-backed country risk.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Ingest Transparency Intl CPI + Basel AML Index | 4h | D8 | internal/ingestion/country_risk.go (new) |
| 2 | Create country_risk_scores table + migration | 2h | D8 | migrations/032_country_risk.sql (new) |
| 3 | Build composite risk index (CPI + Basel + FATF) | 3h | D8-D9 | internal/domain/country_risk.go (new) |
| 4 | Make per-tenant configurable risk overrides | 3h | D9 | internal/domain/tenant_config.go |
| 5 | Add Country Risk section to Configuration page | 2h | D9 | web/src/pages/Configuration.tsx |
| 6 | Table-driven tests + integration test | 2h | D9 | internal/domain/country_risk_test.go (new) |

### Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| PEP classification accuracy | Wrong classification = regulatory exposure | Validate against OpenSanctions known PEPs dataset |
| Audit migration on prod DB | Downtime or data issues | Run migration in transaction, test on staging first |
| Country risk data freshness | CPI/Basel updated annually only | Cache with monthly refresh + manual override capability |

# Sprint 50: UBO Intelligence — Enterprise Blocker

April 28 – May 9, 2026  |  Capacity: 8 days  |  Load: 13 points (81%)

Sprint Goal: Deliver full UBO screening capability — the single biggest enterprise product blocker. Banks cannot onboard corporate clients without beneficial ownership verification.

### Goal 1: UBO Backend API (8 pts) — P0

Domain model exists (internal/domain/ubo.go) but there are no API endpoints, no storage layer, and no screening integration. This sprint builds the full stack.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Create beneficial_owners PostgreSQL table | 2h | D1 | migrations/033_ubo.sql (new) |
| 2 | Implement UBO repository (CRUD + chain query) | 4h | D1-D2 | internal/storage/pgx/ubo_repo.go (new) |
| 3 | Create UBO handler with REST endpoints | 4h | D2 | api/handler_ubo.go (new) |
| 4 | POST /ubo — create/update beneficial owner | 2h | D2 | api/handler_ubo.go |
| 5 | GET /ubo/{org_id} — get ownership chain | 2h | D3 | api/handler_ubo.go |
| 6 | POST /ubo/{org_id}/screen — screen all UBOs | 4h | D3 | api/handler_ubo.go + screening engine |
| 7 | Wire UBO screening into alert generation | 3h | D4 | internal/screening/engine.go |
| 8 | Add UBO routes to router.go | 1h | D4 | api/router.go |
| 9 | Table-driven tests for all UBO endpoints | 4h | D4-D5 | api/handler_ubo_test.go (new) |

### Goal 2: UBO Data Enrichment (5 pts) — P1

Integrate external UBO data sources so customers can auto-populate ownership chains instead of manual entry.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Integrate GLEIF LEI lookup for corporate identity | 4h | D5-D6 | internal/ingestion/gleif.go (new) |
| 2 | Integrate OpenCorporates for ownership data | 4h | D6 | internal/ingestion/opencorporates.go (new) |
| 3 | Build UBO auto-enrichment pipeline | 4h | D7 | internal/ingestion/ubo_enrich.go (new) |
| 4 | Update UBOChain.tsx with real data flow | 3h | D7-D8 | web/src/pages/UBOChain.tsx |
| 5 | Add UBO ownership visualization component | 3h | D8 | web/src/components/UBOTree.tsx (new) |
| 6 | Integration tests with mock external APIs | 2h | D8 | internal/ingestion/gleif_test.go (new) |

### Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| OpenCorporates API rate limits | Can't enrich high-volume UBO lookups | Implement caching layer + batch enrichment queue |
| GLEIF data coverage gaps | Not all entities have LEI codes | Fallback to OpenCorporates + manual entry |
| UBO screening performance | Chain traversal could be slow for deep ownership | Limit traversal to depth=4, async for deeper chains |

# Sprint 51: Maritime Screening + SOC 2 Kickoff

May 12 – May 23, 2026  |  Capacity: 8 days  |  Load: 16 points (100%)

Sprint Goal: Enable vessel screening (closing the maritime gap) and begin SOC 2 Type II certification process.

### Goal 1: Vessel / Maritime Screening (8 pts) — P0

Vessel entity type exists in domain but is explicitly skipped in the OFAC parser. World-Check's Vessel Check is a key add-on for trade finance and maritime banking customers.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Remove vessel/aircraft skip logic in OFAC parser | 1h | D1 | internal/ingestion/ofac.go (line 55-59) |
| 2 | Add vessel-specific fields to Entity (IMO, flag, tonnage) | 3h | D1 | internal/domain/entity.go, vessel.go (new) |
| 3 | Parse vessel data from OFAC SDN format | 4h | D1-D2 | internal/ingestion/ofac_vessel.go (new) |
| 4 | Parse vessel entities from OpenSanctions | 3h | D2 | internal/ingestion/opensanctions.go |
| 5 | Build vessel screening endpoint (POST /vessel/screen) | 4h | D3 | api/handler_vessel.go (new) |
| 6 | Create VesselScreening.tsx page | 4h | D3-D4 | web/src/pages/VesselScreening.tsx (new) |
| 7 | Add vessel entity type to search/filter UI | 2h | D4 | web/src/components/SearchField.tsx |
| 8 | Vessel-specific matching rules (IMO exact, name fuzzy) | 3h | D4 | internal/screening/vessel_matcher.go (new) |
| 9 | Table-driven tests for vessel screening | 3h | D5 | api/handler_vessel_test.go (new) |

### Goal 2: SOC 2 Type II — Phase 1 (8 pts) — P0

SOC 2 certification is critical for enterprise sales credibility. Sprint 47 completed documentation; this sprint begins the formal audit process.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Select SOC 2 auditor (Vanta/Drata + CPA firm) | 4h | D5 | docs/compliance/ (vendor evaluation) |
| 2 | Complete readiness assessment questionnaire | 4h | D6 | docs/compliance/soc2_readiness.md (new) |
| 3 | Implement automated evidence collection scripts | 4h | D6-D7 | scripts/soc2_evidence.sh (new) |
| 4 | Set up continuous monitoring (uptime, access logs) | 4h | D7 | internal/security/continuous_monitor.go (new) |
| 5 | Remediate any gaps found in readiness assessment | 4h | D7-D8 | Various based on findings |
| 6 | Document change management procedure | 2h | D8 | docs/compliance/change_management.md (new) |
| 7 | Begin 3-month observation window | 1h | D8 | Calendar + auditor kickoff |

### Risks

| Risk | Impact | Mitigation |
| --- | --- | --- |
| OFAC vessel data quality | Vessel names may not match format expected | Test against OFAC SDN vessel sample set first |
| SOC 2 auditor availability | 3-6 month waitlist at some firms | Contact 3 firms simultaneously, use Vanta for automation |
| Scope creep on SOC 2 gaps | Readiness assessment may surface major issues | Timebox remediation to 4h; defer non-critical to next sprint |

# Sprint 52: Data Depth + SOC 2 Finalization

May 26 – June 6, 2026  |  Capacity: 8 days  |  Load: 13 points (81%)

Sprint Goal: Close the data depth gap via OpenSanctions partnership and finalize SOC 2 evidence collection. Ship the complete competitive gap closure.

### Goal 1: Data Depth — OpenSanctions Premium Partnership (5 pts) — P0

World-Check has 4M+ records from 400 human analysts. We can't replicate that team, but we can dramatically expand coverage via OpenSanctions Premium tier + additional data sources.

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Negotiate OpenSanctions Premium API access | 4h | D1 | External — partnership agreement |
| 2 | Integrate Premium PEP dataset (expanded coverage) | 4h | D1-D2 | internal/ingestion/opensanctions.go |
| 3 | Add EveryPolitician dataset for deeper PEP coverage | 3h | D2 | internal/ingestion/everypolitician.go (new) |
| 4 | Integrate ICIJ Offshore Leaks for UBO enrichment | 3h | D3 | internal/ingestion/icij.go (new) |
| 5 | Build data coverage dashboard (list health, freshness) | 4h | D3-D4 | web/src/pages/DataCoverage.tsx (new) |
| 6 | Update marketing: publish data source count on site | 2h | D4 | web/src/pages/ProductShowcase.tsx |

### Goal 2: SOC 2 — Phase 2 + Final QA (5 pts) — P0

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | Complete evidence collection for Trust Services Criteria | 4h | D5 | docs/compliance/soc2_evidence/ |
| 2 | Validate all controls are operating effectively | 3h | D5-D6 | scripts/soc2_evidence.sh |
| 3 | Remediate final audit findings | 4h | D6 | Various based on findings |
| 4 | Submit initial evidence package to auditor | 2h | D7 | External — auditor portal |

### Goal 3: Integration Testing + Release (3 pts) — P0

| # | Task | Est. | Day | Files |
| --- | --- | --- | --- | --- |
| 1 | End-to-end integration test of all new features | 4h | D7 | scripts/test-integration.sh |
| 2 | Performance regression test (<50ms target) | 2h | D8 | scripts/benchmark.sh |
| 3 | Update docs: SCREENING_ENGINE.md, API_REFERENCE.md, CODE_MAP.md | 3h | D8 | docs/ |
| 4 | Update VISION.md competitive table with closed gaps | 1h | D8 | docs/VISION.md |

# Global Definition of Done

Every task across all 4 sprints must meet these criteria before being marked complete:

| ☐ | Criterion |
| --- | --- |
| ☐ | Code reviewed (self-review for solo; checklist-based) |
| ☐ | Table-driven tests written and passing (Go: go test ./...; React: npm test) |
| ☐ | Files ≤ 100 lines (split if approaching limit per CLAUDE.md rules) |
| ☐ | No panic() in production code — return errors |
| ☐ | No TODO comments without issue link |
| ☐ | All exported types have methods (no bare structs) |
| ☐ | Database queries wrapped in repository interfaces |
| ☐ | React components use hooks (no class components) |
| ☐ | Documentation updated (API_REFERENCE.md, CODE_MAP.md as needed) |
| ☐ | Performance: screening endpoint still <50ms p95 |

# Sprint Timeline Summary

| Week | Sprint 49 | Sprint 50 | Sprint 51 | Sprint 52 |
| --- | --- | --- | --- | --- |
| 1-2 | PEP Sub-Class + Audit Logs + Country Risk |  |  |  |
| 3-4 |  | UBO API + GLEIF/OpenCorp Enrichment |  |  |
| 5-6 |  |  | Vessel Screening + SOC 2 Phase 1 |  |
| 7-8 |  |  |  | Data + SOC2 + QA |

After Sprint 52: AMLIQ matches or beats World-Check on 13 of 14 services. The only remaining gap is Screening Resolution Service (managed analyst outsourcing) — which we counter-position with AI-powered match explanations. All 7 competitive gaps CLOSED.

## Success Metrics (Post-Sprint 52)

| Metric | Target | How to Measure |
| --- | --- | --- |
| PEP classification accuracy | ≥95% vs OpenSanctions labels | Run classifier against labeled PEP dataset |
| UBO API latency (chain query) | <200ms for depth-4 chains | Load test with 100 concurrent chain lookups |
| Vessel match precision | ≥90% true positive rate | Test against OFAC SDN vessel list |
| Country risk coverage | 240+ countries scored | Count unique country codes in risk table |
| Audit log durability | Zero dropped events under load | Load test: 10k events/min sustained |
| Test suite health | All tests green, 0 regressions | CI pipeline: go test + npm test |
| SOC 2 readiness score | ≥80% on readiness assessment | Auditor readiness report |