## Executive Overview
QESTRO — MARKET DOMINATION SPRINT PLAN
The Vibe Coding Test Pilot ¦ April-September 2026 ¦ 6 Sprints to Rule the Market
MISSION: Become the #1 AI testing platform for the vibe coding era. Every developer who vibes code uses Qestro to test.
MARKET INTELLIGENCE
Metric | What It Means | Context
$2.74B | AI Testing Market by 2030 | $736M in 2023
85% | Developers Using AI Tools Daily | Up from 51% in 2024
46% | Code Now AI-Generated (Copilot) | 96% don't fully trust it
2,300+ | MCP Servers in Public Dirs | Universal AI integration
$8.5B | Vibe Coding Market in 2026 | Testing is the bottleneck
1.7x | More Bugs in AI-Written Code | Massive QA demand
COMPETITIVE MOAT: WHY QESTRO WINS
Moat | Description | Why It Matters | Type
Vibe Test Pilot | Only platform purpose-built for vibe-coded apps. Paste URL → AI generates full test suite. | No competitor does this | UNIQUE
MCP-Native Testing | First testing tool with MCP server. Any AI IDE (Cursor, Windsurf, Claude Code) runs Qestro tests natively. | 2,300+ MCP tools ecosystem | FIRST MOVER
Self-Healing Engine | AI fixes broken selectors, timing issues, API changes automatically. Zero-maintenance tests. | Saves 40+ hrs/month per team | MOAT
Unified Platform | Browser + Mobile + API testing in one tool. Playwright + Maestro + Axios orchestrated. | Competitors do 1-2, not all 3 | ADVANTAGE
Open-Source Core | CLI + test runner open-source. Viral adoption through GitHub. Cloud for dashboards & CI. | Community-driven growth | VIRAL
Qestro Score Badge | Public test health badge for repos. Social proof. Developers display it like coverage badges. | Network effect flywheel | VIRAL
6-SPRINT ROADMAP (April — September 2026)
Sprint | Dates | Theme | Key Deliverables | Priority
Sprint 1 | Apr 7-20 | Foundation & Launch Prep | Production deploy, Docker, CI/CD, auth (SSO), real DB | CRITICAL
Sprint 2 | Apr 21-May 4 | Vibe Test Pilot MVP | URL → AI test gen, MCP server, CLI open-source, Qestro Score | CRITICAL
Sprint 3 | May 5-18 | Self-Healing & Mobile | Self-healing v2, Maestro mobile, visual regression, cross-browser | HIGH
Sprint 4 | May 19-Jun 1 | Growth Engine | GitHub Action, VS Code extension, Qestro Score badges, landing page | HIGH
Sprint 5 | Jun 2-15 | Enterprise & Scale | SSO/SAML, team workspaces, RBAC, audit logs, SOC2 prep | MEDIUM
Sprint 6 | Jun 16-29 | Market Domination | Plugin marketplace, load testing, desktop agent, public launch | MEDIUM
SUCCESS METRICS (End of 6 Sprints)
Metric | Current | Target (Sep 2026) | Why It Matters
GitHub Stars | 0 | 2,000+ | Open-source CLI adoption
MCP Installs | 0 | 500+ | AI IDE integration
Registered Users | 0 | 1,000+ | Platform signups
Paying Customers | 0 | 50+ | Revenue validation
Test Runs/Month | 0 | 100,000+ | Platform usage
Monthly Revenue | $0 | $15,000+ | ARR trajectory to $180K+
NPS Score | N/A | 60+ | User satisfaction
Avg Tests Generated/User | 0 | 25+ | Stickiness metric

## Sprint 1 — Foundation
SPRINT 1 — FOUNDATION
April 7-20, 2026
GOAL: Ship production-ready infrastructure. Real database, real auth, real deploy. No more mocks.
Day 1 - Mon Apr 7
Task | Area | Description | File/Location | Est. | Priority
Docker Compose production setup | DevOps | Configure Postgres 16 + Redis 7 + app containers | docker-compose.prod.yml | 4h | CRITICAL
Environment variable system | Backend | Centralize all config: DB, Redis, JWT, API keys, SMTP | shared/config/env.ts | 2h | CRITICAL
Database migration runner | Backend | Drizzle ORM migrate command for 66 tables | drizzle/migrations/ | 2h | CRITICAL
Day 2 - Tue Apr 8
Task | Area | Description | File/Location | Est. | Priority
Real JWT auth implementation | Backend | Replace mock tokens with jsonwebtoken + refresh rotation | backend/src/middleware/auth.ts | 4h | CRITICAL
Password hashing with argon2 | Backend | Secure password storage, bcrypt alternative | backend/src/services/auth.ts | 2h | CRITICAL
User registration with email verification | Backend | Signup → verify email → activate account flow | backend/src/controllers/authController.ts | 2h | HIGH
Day 3 - Wed Apr 9
Task | Area | Description | File/Location | Est. | Priority
SSO/OAuth2 — Google login | Backend | Google OAuth2 PKCE flow for one-click signup | backend/src/services/sso.ts | 3h | HIGH
SSO/OAuth2 — GitHub login | Backend | GitHub OAuth for developer-first experience | backend/src/services/sso.ts | 2h | HIGH
Frontend auth store → real API | Frontend | Remove all mock bypasses, connect to real JWT flow | frontend/src/stores/authStore.ts | 3h | CRITICAL
Day 4 - Thu Apr 10
Task | Area | Description | File/Location | Est. | Priority
Real dashboard API endpoints | Backend | Wire dashboard stats to actual DB queries (Drizzle) | backend/src/controllers/dashboard.ts | 4h | HIGH
Projects CRUD → real DB | Backend | Create/read/update/delete projects with Drizzle ORM | backend/src/controllers/projects.ts | 3h | HIGH
API error handling middleware | Backend | Consistent error responses, validation, rate limiting | backend/src/middleware/error.ts | 1h | MEDIUM
Day 5 - Fri Apr 11
Task | Area | Description | File/Location | Est. | Priority
Test cases CRUD → real DB | Backend | Full test case lifecycle backed by PostgreSQL | backend/src/controllers/testCases.ts | 4h | HIGH
Test plans CRUD → real DB | Backend | Test plan management with test case associations | backend/src/controllers/testPlans.ts | 3h | HIGH
Unit tests: auth + CRUD | Testing | Jest tests for all new real endpoints (target 85%) | backend/tests/ | 1h | HIGH
Day 6-7 - Sat-Sun Apr 12-13
Task | Area | Description | File/Location | Est. | Priority
Bull queue → real Redis | Backend | Connect test execution queue to production Redis | backend/src/queue/test-job.queue.ts | 3h | HIGH
Test execution pipeline (real) | Backend | Job → runner selection → execute → store results | backend/src/services/test-engine.ts | 4h | CRITICAL
Integration tests | Testing | E2E: signup → create project → create test → run | tests/integration/ | 3h | HIGH
Day 8 - Mon Apr 14
Task | Area | Description | File/Location | Est. | Priority
CI/CD pipeline — GitHub Actions | DevOps | Build → test → lint → Docker build → push to registry | .github/workflows/ci.yml | 3h | HIGH
Staging environment setup | DevOps | Deploy to staging (Railway/Render/Fly.io) | k8s/ or railway.toml | 3h | HIGH
Health monitoring + alerts | DevOps | Uptime checks, error alerts (Sentry or Axiom) | backend/src/utils/monitoring.ts | 2h | MEDIUM
Day 9 - Tue Apr 15
Task | Area | Description | File/Location | Est. | Priority
Frontend build pipeline fix | Frontend | Fix Vite build, remove hardcoded API URLs, env injection | frontend/vite.config.ts | 2h | CRITICAL
Frontend → staging deploy | Frontend | Deploy frontend to Vercel/Netlify with env vars | frontend/vercel.json | 2h | HIGH
Real WebSocket for live results | Backend | Socket.io for real-time test execution updates | backend/src/services/websocket.ts | 4h | MEDIUM
Day 10 - Wed Apr 16
Task | Area | Description | File/Location | Est. | Priority
Playwright runner → production | Backend | Real Playwright execution in Docker container | playwright-service/Dockerfile | 4h | CRITICAL
Screenshot capture + storage | Backend | Save screenshots to S3/R2, serve via signed URLs | backend/src/services/storage.ts | 3h | HIGH
Test result viewer (real data) | Frontend | Display real test results with screenshots, logs, timing | frontend/src/pages/TestResults.tsx | 1h | HIGH
Day 11 - Thu Apr 17
Task | Area | Description | File/Location | Est. | Priority
Email service (Resend/SES) | Backend | Transactional emails: verify, invite, alerts, reports | backend/src/services/email.ts | 3h | MEDIUM
Team invite system | Backend | Invite users to workspace via email, accept/decline | backend/src/controllers/teams.ts | 3h | MEDIUM
Billing integration (Stripe) | Backend | Stripe Checkout + webhooks for subscription management | backend/src/services/billing.ts | 2h | HIGH
Day 12 - Fri Apr 18
Task | Area | Description | File/Location | Est. | Priority
Stripe pricing page | Frontend | Free/Starter/Pro/Enterprise tiers with Stripe Checkout | frontend/src/pages/Pricing.tsx | 3h | HIGH
Usage metering | Backend | Track test runs, AI generations, storage per user | backend/src/services/usage.ts | 3h | HIGH
Rate limiting per plan | Backend | Enforce limits: free=100 runs, starter=1000, pro=unlimited | backend/src/middleware/rateLimiter.ts | 2h | MEDIUM
Day 13-14 - Sat-Sun Apr 19-20
Task | Area | Description | File/Location | Est. | Priority
Full E2E test suite | Testing | Playwright E2E: auth, dashboard, projects, test creation, execution | tests/*.spec.ts | 4h | HIGH
Load testing baseline | Testing | k6 load test: 100 concurrent users, measure response times | tests/load/ | 2h | MEDIUM
Sprint 1 retrospective + bug fixes | All | Fix all P0/P1 bugs found during testing | Various | 4h | CRITICAL
DEPLOY TO PRODUCTION | DevOps | Push to production domain: app.qestro.io | k8s/ or deploy script | 2h | CRITICAL
SPRINT TOTALS: 37 tasks ¦ 11 CRITICAL ¦ 19 HIGH ¦ 7 MEDIUM/LOW

## Sprint 2 — Vibe Pilot
SPRINT 2 — VIBE PILOT
April 21 - May 4, 2026
GOAL: Launch the Vibe Test Pilot: paste a URL → AI generates a full test suite. Ship MCP server + open-source CLI.
Day 1 - Mon Apr 21
Task | Area | Description | File/Location | Est. | Priority
URL crawler agent | AI/Backend | Crawl target URL: extract routes, forms, buttons, API calls | orchestrator/src/generators/crawler.ts | 4h | CRITICAL
Page analyzer (DOM → test hints) | AI/Backend | Analyze page structure: interactive elements, user flows | orchestrator/src/generators/analyzer.ts | 3h | CRITICAL
Sitemap discovery | AI/Backend | Auto-discover pages via sitemap.xml, robots.txt, link following | orchestrator/src/generators/sitemap.ts | 1h | HIGH
Day 2 - Tue Apr 22
Task | Area | Description | File/Location | Est. | Priority
LLM test generation engine v2 | AI/Backend | Claude/GPT → Playwright test code from page analysis | orchestrator/src/generators/test-generator.ts | 4h | CRITICAL
Prompt engineering: test quality | AI | Craft prompts that generate robust, non-flaky tests | orchestrator/src/generators/prompts/ | 2h | CRITICAL
Test code validator | AI/Backend | Parse generated code, type-check, dry-run before saving | orchestrator/src/generators/validator.ts | 2h | HIGH
Day 3 - Wed Apr 23
Task | Area | Description | File/Location | Est. | Priority
Vibe Test Pilot UI | Frontend | Paste URL → progress bar → generated tests appear in editor | frontend/src/pages/VibePilot.tsx | 4h | CRITICAL
Test editor with AI suggestions | Frontend | Monaco editor with inline AI fix suggestions | frontend/src/components/TestEditor.tsx | 3h | HIGH
Natural language test refinement | Frontend | Chat interface: 'add login test' → AI modifies suite | frontend/src/components/TestChat.tsx | 1h | HIGH
Day 4 - Thu Apr 24
Task | Area | Description | File/Location | Est. | Priority
MCP server implementation | Backend | Qestro MCP server: tools for test gen, run, results | mcp-server/src/index.ts | 4h | CRITICAL
MCP tools: generate_tests | Backend | MCP tool: generate tests from URL or description | mcp-server/src/tools/generate.ts | 2h | CRITICAL
MCP tools: run_tests, get_results | Backend | MCP tools: execute tests, fetch results | mcp-server/src/tools/run.ts | 2h | HIGH
Day 5 - Fri Apr 25
Task | Area | Description | File/Location | Est. | Priority
CLI tool v2 (open-source) | CLI | qestro init, qestro generate <url>, qestro run, qestro report | cli/src/commands/ | 4h | CRITICAL
CLI → MCP bridge | CLI | CLI uses MCP protocol to communicate with Qestro cloud | cli/src/mcp-client.ts | 2h | HIGH
npm publish setup | CLI | Package as @qestro/cli on npm, auto-publish via CI | cli/package.json | 2h | HIGH
Day 6-7 - Sat-Sun Apr 26-27
Task | Area | Description | File/Location | Est. | Priority
API test generation | AI/Backend | Analyze OpenAPI/Swagger spec → generate API tests | orchestrator/src/generators/api-gen.ts | 4h | HIGH
GraphQL test generation | AI/Backend | Introspect GraphQL schema → generate query/mutation tests | orchestrator/src/generators/graphql-gen.ts | 3h | MEDIUM
Test generation quality benchmark | Testing | Run against 20 popular websites, measure test quality | tests/benchmarks/ | 3h | HIGH
Day 8 - Mon Apr 28
Task | Area | Description | File/Location | Est. | Priority
Qestro Score algorithm | Backend | Calculate test health score: coverage, pass rate, freshness | backend/src/services/qestro-score.ts | 3h | HIGH
Qestro Score badge SVG generator | Backend | Dynamic SVG badge like shields.io for README display | backend/src/controllers/badge.ts | 2h | HIGH
Public score page | Frontend | Public URL showing project's Qestro Score + trends | frontend/src/pages/PublicScore.tsx | 3h | MEDIUM
Day 9 - Tue Apr 29
Task | Area | Description | File/Location | Est. | Priority
GitHub App integration | Backend | Install Qestro on repos, auto-run tests on PR | backend/src/services/github-app.ts | 4h | HIGH
PR comment with results | Backend | Post test results as GitHub PR comment with badge | backend/src/services/github-pr.ts | 2h | HIGH
GitHub Action (marketplace) | DevOps | qestro/test-action: run Qestro tests in any CI pipeline | .github/actions/test/action.yml | 2h | HIGH
Day 10 - Wed Apr 30
Task | Area | Description | File/Location | Est. | Priority
Landing page v2 | Frontend | Marketing site: hero, demo video, pricing, testimonials | frontend/src/pages/Landing.tsx | 4h | HIGH
Interactive demo (no signup) | Frontend | Try Qestro: paste URL, see generated tests live | frontend/src/pages/Demo.tsx | 3h | CRITICAL
SEO + Open Graph meta | Frontend | Meta tags, OG images, structured data for search | frontend/src/app/layout.tsx | 1h | MEDIUM
Day 11 - Thu May 1
Task | Area | Description | File/Location | Est. | Priority
Onboarding wizard | Frontend | First-time user: connect repo → paste URL → first test → run | frontend/src/components/Onboarding.tsx | 4h | HIGH
Usage analytics (PostHog/Mixpanel) | Frontend | Track: test created, test run, feature used, churn signals | frontend/src/lib/analytics.ts | 2h | HIGH
Feedback widget | Frontend | In-app feedback: thumbs up/down + comment on every page | frontend/src/components/Feedback.tsx | 2h | MEDIUM
Day 12 - Fri May 2
Task | Area | Description | File/Location | Est. | Priority
Documentation site | Docs | docs.qestro.io: getting started, CLI, MCP, API reference | docs/ | 4h | HIGH
Video tutorial: Vibe Test Pilot | Marketing | 2-min demo video: URL → tests → run → results | assets/videos/ | 2h | HIGH
Blog post: 'Testing for Vibe Coders' | Marketing | SEO content: why vibe coding needs Qestro | blog/ | 2h | MEDIUM
Day 13-14 - Sat-Sun May 3-4
Task | Area | Description | File/Location | Est. | Priority
Full regression test suite | Testing | E2E all Sprint 2 features: vibe pilot, MCP, CLI, score | tests/*.spec.ts | 3h | HIGH
Performance benchmark | Testing | Test gen latency <10s, test run <30s, dashboard <500ms | tests/performance/ | 2h | HIGH
PUBLIC BETA LAUNCH | All | Announce on HN, Twitter/X, Reddit, Product Hunt prep | Various | 3h | CRITICAL
Sprint 2 retrospective + hotfixes | All | Fix launch-day bugs, monitor error rates | Various | 2h | CRITICAL
SPRINT TOTALS: 37 tasks ¦ 11 CRITICAL ¦ 21 HIGH ¦ 5 MEDIUM/LOW

## Sprint 3 — Self-Heal & Mobile
SPRINT 3 — SELF-HEAL & MOBILE
May 5-18, 2026
GOAL: Self-healing v2 (AI fixes tests automatically), full mobile testing, visual regression. Zero-maintenance testing.
Day 1 - Mon May 5
Task | Area | Description | File/Location | Est. | Priority
Self-healing engine v2 | AI/Backend | AI analyzes failure screenshot + DOM diff → auto-fix selector | backend/src/services/SelfHealingEngine.ts | 4h | CRITICAL
Timing healer | AI/Backend | Detect and fix flaky timing issues (waits, animations) | orchestrator/src/healers/timing-healer.ts | 2h | HIGH
API response healer | AI/Backend | Detect API schema changes, update assertions automatically | orchestrator/src/healers/api-healer.ts | 2h | HIGH
Day 2 - Tue May 6
Task | Area | Description | File/Location | Est. | Priority
Visual regression engine | Backend | Pixel-diff screenshots: baseline vs current, highlight changes | backend/src/services/visual-regression.ts | 4h | CRITICAL
Visual diff UI | Frontend | Side-by-side screenshot comparison with diff overlay | frontend/src/components/VisualDiff.tsx | 3h | HIGH
Baseline management | Backend | Accept/reject visual changes, update baselines per branch | backend/src/controllers/baselines.ts | 1h | HIGH
Day 3 - Wed May 7
Task | Area | Description | File/Location | Est. | Priority
Maestro mobile runner (real) | Backend | Execute Maestro scripts on iOS/Android simulators | orchestrator/src/runners/maestro.ts | 4h | CRITICAL
Mobile test generation | AI/Backend | Generate Maestro YAML from app description + screenshots | orchestrator/src/generators/mobile-gen.ts | 3h | HIGH
Device farm integration | Backend | Connect to BrowserStack/Sauce Labs for real devices | backend/src/services/device-farm.ts | 1h | MEDIUM
Day 4 - Thu May 8
Task | Area | Description | File/Location | Est. | Priority
Cross-browser matrix | Backend | Run tests across Chrome, Firefox, Safari, Edge in parallel | orchestrator/src/runners/browser-matrix.ts | 3h | HIGH
Parallel test execution | Backend | Shard tests across multiple workers for speed | backend/src/services/test-sharding.ts | 3h | HIGH
Test execution dashboard v2 | Frontend | Real-time parallel execution view with browser icons | frontend/src/pages/ExecutionDashboard.tsx | 2h | MEDIUM
Day 5 - Fri May 9
Task | Area | Description | File/Location | Est. | Priority
Flakiness detection algorithm | Backend | Track test stability over runs, flag flaky tests | backend/src/services/AnalyticsEngine.ts | 3h | HIGH
Auto-retry with healing | Backend | Failed test → self-heal → retry → report delta | orchestrator/src/healers/retry-healer.ts | 3h | HIGH
Healing report UI | Frontend | Show what was healed, before/after, confidence score | frontend/src/components/HealingReport.tsx | 2h | MEDIUM
Day 6-7 - Sat-Sun May 10-11
Task | Area | Description | File/Location | Est. | Priority
Accessibility testing module | Backend | axe-core integration: WCAG 2.1 AA checks on every test run | orchestrator/src/runners/a11y-runner.ts | 3h | MEDIUM
Performance metrics capture | Backend | Capture Core Web Vitals (LCP, FID, CLS) during test runs | orchestrator/src/runners/perf-runner.ts | 3h | MEDIUM
Security scan module | Backend | Basic OWASP checks: XSS, injection, headers during test runs | orchestrator/src/runners/security-runner.ts | 2h | MEDIUM
Unit + integration tests | Testing | 85% coverage on all new Sprint 3 code | tests/ | 2h | HIGH
Day 8 - Mon May 12
Task | Area | Description | File/Location | Est. | Priority
Webhook notifications | Backend | Slack/Discord/Teams webhooks on test completion | backend/src/services/webhooks.ts | 3h | HIGH
Email report scheduling | Backend | Daily/weekly email digest of test results | backend/src/services/report-scheduler.ts | 2h | MEDIUM
Notification preferences UI | Frontend | Configure per-project notification channels and triggers | frontend/src/pages/Notifications.tsx | 3h | MEDIUM
Day 9 - Tue May 13
Task | Area | Description | File/Location | Est. | Priority
Test recording v2 (browser) | Frontend | Record user actions in browser → generate Playwright code | frontend/src/components/Recorder.tsx | 4h | HIGH
Recording → test code converter | Backend | Convert recorded actions to clean, maintainable test code | orchestrator/src/generators/recording-converter.ts | 3h | HIGH
Recording playback viewer | Frontend | Replay recorded sessions with action timeline | frontend/src/components/RecordingPlayer.tsx | 1h | MEDIUM
Day 10 - Wed May 14
Task | Area | Description | File/Location | Est. | Priority
Test tagging and filtering | Backend | Tags: smoke, regression, critical. Filter and run subsets | backend/src/controllers/testCases.ts | 2h | MEDIUM
Test suite organization | Frontend | Drag-and-drop test organization, folders, smart groups | frontend/src/components/TestSuiteTree.tsx | 3h | MEDIUM
Bulk operations | Frontend | Multi-select tests: run, tag, move, delete, assign | frontend/src/components/BulkActions.tsx | 3h | MEDIUM
Day 11 - Thu May 15
Task | Area | Description | File/Location | Est. | Priority
Analytics dashboard v2 | Frontend | Trends, flakiness heatmap, slowest tests, coverage gaps | frontend/src/pages/AnalyticsDashboard.tsx | 4h | HIGH
Export reports (PDF, JUnit, CSV) | Backend | Generate downloadable reports in multiple formats | backend/src/services/report-generator.ts | 3h | HIGH
CI/CD result aggregation | Backend | Aggregate results across branches, envs, time periods | backend/src/services/aggregation.ts | 1h | MEDIUM
Day 12 - Fri May 16
Task | Area | Description | File/Location | Est. | Priority
API testing UI | Frontend | Visual API test builder: method, URL, headers, body, assertions | frontend/src/pages/APITesting.tsx | 4h | HIGH
Request chaining UI | Frontend | Visual flow: Login → Get token → Use in next request | frontend/src/components/RequestChain.tsx | 3h | MEDIUM
Environment variables UI | Frontend | Manage env vars per environment (dev, staging, prod) | frontend/src/pages/Environments.tsx | 1h | MEDIUM
Day 13-14 - Sat-Sun May 17-18
Task | Area | Description | File/Location | Est. | Priority
Full regression + mobile E2E | Testing | Test all features on Chrome, Firefox, Safari + iOS, Android | tests/ | 4h | HIGH
Self-healing accuracy benchmark | Testing | Run against 50 intentionally broken tests, measure fix rate | tests/benchmarks/healing/ | 2h | HIGH
Visual regression baseline set | Testing | Capture baselines for all pages, both themes | tests/visual/ | 2h | HIGH
Sprint 3 retrospective + fixes | All | Fix all P0/P1 bugs, performance tuning | Various | 2h | CRITICAL
SPRINT TOTALS: 38 tasks ¦ 4 CRITICAL ¦ 19 HIGH ¦ 15 MEDIUM/LOW

## Sprint 4 — Growth Engine
SPRINT 4 — GROWTH ENGINE
May 19 - June 1, 2026
GOAL: Viral growth: GitHub Action, VS Code extension, Qestro Score badges, Product Hunt launch, content marketing.
Day 1 - Mon May 19
Task | Area | Description | File/Location | Est. | Priority
VS Code extension | Frontend | Run Qestro tests from VS Code, inline results, AI suggestions | vscode-extension/src/ | 4h | CRITICAL
Extension: test generation inline | Frontend | Right-click file → Generate Qestro tests | vscode-extension/src/commands/ | 2h | HIGH
Extension marketplace publish | DevOps | Publish to VS Code Marketplace with icons, README | vscode-extension/package.json | 2h | HIGH
Day 2 - Tue May 20
Task | Area | Description | File/Location | Est. | Priority
Cursor/Windsurf MCP integration guide | Docs | Step-by-step: install Qestro MCP in Cursor/Windsurf | docs/integrations/ | 2h | HIGH
Claude Code MCP integration | Docs | qestro MCP server for Claude Code users | docs/integrations/claude-code.md | 2h | HIGH
MCP server v2: advanced tools | Backend | Add: heal_test, get_score, compare_branches, schedule | mcp-server/src/tools/ | 4h | HIGH
Day 3 - Wed May 21
Task | Area | Description | File/Location | Est. | Priority
GitHub Action v2 (marketplace) | DevOps | One-line CI integration: uses: qestro/test@v1 | .github/actions/ | 3h | CRITICAL
GitLab CI template | DevOps | Include template for GitLab CI/CD pipelines | ci-templates/gitlab/ | 2h | HIGH
Bitbucket Pipes integration | DevOps | Bitbucket Pipes template for Qestro tests | ci-templates/bitbucket/ | 2h | MEDIUM
Day 4 - Thu May 22
Task | Area | Description | File/Location | Est. | Priority
Product Hunt launch prep | Marketing | PH page, screenshots, GIF demo, maker story, hunter outreach | marketing/ | 4h | CRITICAL
Demo video production | Marketing | 3-min polished demo: URL → tests → PR comment → badge | assets/videos/ | 3h | HIGH
Social media assets | Marketing | Twitter/X, LinkedIn, Reddit graphics and copy | marketing/social/ | 1h | MEDIUM
Day 5 - Fri May 23
Task | Area | Description | File/Location | Est. | Priority
PRODUCT HUNT LAUNCH DAY | Marketing | Launch on PH, respond to comments, share on social | Various | 8h | CRITICAL
Day 6-7 - Sat-Sun May 24-25
Task | Area | Description | File/Location | Est. | Priority
Post-launch bug triage | All | Fix bugs reported by PH users within 24h | Various | 4h | CRITICAL
User feedback analysis | Product | Categorize feedback, prioritize feature requests | Various | 2h | HIGH
Conversion optimization | Frontend | Improve signup → first test → aha moment funnel | frontend/src/ | 4h | HIGH
Day 8 - Mon May 26
Task | Area | Description | File/Location | Est. | Priority
Referral system | Backend | Invite friends → both get bonus test runs | backend/src/services/referral.ts | 3h | HIGH
Template gallery | Backend | Pre-built test templates: e-commerce, SaaS, auth, API | backend/src/services/templates.ts | 3h | HIGH
Community templates | Frontend | Browse, fork, share test templates from community | frontend/src/pages/Templates.tsx | 2h | MEDIUM
Day 9 - Tue May 27
Task | Area | Description | File/Location | Est. | Priority
SEO content: 10 blog posts | Marketing | AI testing guides, comparisons, tutorials for organic traffic | blog/ | 4h | HIGH
YouTube tutorial series | Marketing | 5 tutorial videos: getting started, CLI, MCP, API, mobile | assets/videos/ | 3h | MEDIUM
Developer community setup | Marketing | Discord server with channels: help, showcase, feedback | Various | 1h | HIGH
Day 10 - Wed May 28
Task | Area | Description | File/Location | Est. | Priority
Comparison pages | Marketing | Qestro vs Cypress, vs Playwright, vs TestMu, vs Momentic | frontend/src/pages/Compare.tsx | 4h | HIGH
ROI calculator | Frontend | Interactive: 'How much time will Qestro save your team?' | frontend/src/pages/ROI.tsx | 3h | MEDIUM
Case study template | Marketing | Template for documenting early customer success stories | marketing/case-studies/ | 1h | MEDIUM
Day 11 - Thu May 29
Task | Area | Description | File/Location | Est. | Priority
Slack bot for Qestro | Backend | Slash commands: /qestro run, /qestro status, /qestro score | backend/src/services/slack-bot.ts | 4h | MEDIUM
Discord bot | Backend | Same commands for Discord developer communities | backend/src/services/discord-bot.ts | 3h | MEDIUM
Zapier/Make integration | Backend | No-code automation: trigger tests on any event | backend/src/services/zapier.ts | 1h | LOW
Day 12 - Fri May 30
Task | Area | Description | File/Location | Est. | Priority
A/B testing framework (internal) | Frontend | Test different onboarding flows, pricing pages, CTAs | frontend/src/lib/ab-test.ts | 3h | MEDIUM
User segmentation | Backend | Segment users: solo dev, team lead, enterprise, QA engineer | backend/src/services/segmentation.ts | 2h | MEDIUM
Personalized onboarding | Frontend | Different onboarding paths per persona | frontend/src/components/Onboarding.tsx | 3h | HIGH
Day 13-14 - Sat-Sun May 31-Jun 1
Task | Area | Description | File/Location | Est. | Priority
Growth metrics dashboard (internal) | Backend | Track: signups, activation, retention, revenue, NPS | backend/src/services/growth-metrics.ts | 3h | HIGH
Automated drip email campaign | Marketing | Day 0,1,3,7 emails: welcome → tips → upgrade → win-back | backend/src/services/email-drip.ts | 3h | MEDIUM
Sprint 4 retrospective | All | Review PH results, user feedback, conversion rates | Various | 2h | HIGH
Growth playbook documentation | All | Document what worked, what didn't, playbook for next sprint | docs/internal/growth-playbook.md | 2h | MEDIUM
SPRINT TOTALS: 35 tasks ¦ 5 CRITICAL ¦ 17 HIGH ¦ 13 MEDIUM/LOW

## Sprint 5 — Enterprise
SPRINT 5 — ENTERPRISE
June 2-15, 2026
GOAL: Enterprise features: SSO/SAML, RBAC, audit logs, team workspaces, SOC2 preparation. Land first enterprise deal.
Day 1 - Mon Jun 2
Task | Area | Description | File/Location | Est. | Priority
SAML SSO — Azure AD | Backend | SAML 2.0 integration for Azure AD enterprise login | backend/src/services/saml.ts | 4h | CRITICAL
SAML SSO — Okta | Backend | Okta SAML integration for enterprise customers | backend/src/services/saml.ts | 3h | CRITICAL
SSO admin configuration UI | Frontend | Enterprise admin: configure SAML provider, test connection | frontend/src/pages/admin/SSO.tsx | 1h | HIGH
Day 2 - Tue Jun 3
Task | Area | Description | File/Location | Est. | Priority
RBAC system | Backend | Roles: owner, admin, editor, viewer. Per-project permissions | backend/src/services/rbac.ts | 4h | CRITICAL
Team workspace isolation | Backend | Multi-tenant: each org has isolated data, settings, billing | backend/src/services/workspace.ts | 3h | CRITICAL
Team management UI | Frontend | Invite, remove, change roles, manage permissions | frontend/src/pages/TeamSettings.tsx | 1h | HIGH
Day 3 - Wed Jun 4
Task | Area | Description | File/Location | Est. | Priority
Audit log system | Backend | Log every action: who, what, when, IP. Immutable audit trail | backend/src/services/audit.ts | 4h | HIGH
Audit log viewer | Frontend | Searchable, filterable audit log for compliance officers | frontend/src/pages/AuditLog.tsx | 3h | HIGH
Data retention policies | Backend | Configurable retention: 30/60/90/365 days per org | backend/src/services/retention.ts | 1h | MEDIUM
Day 4 - Thu Jun 5
Task | Area | Description | File/Location | Est. | Priority
API key management | Backend | Generate, rotate, revoke API keys per user/service account | backend/src/controllers/apiKeys.ts | 3h | HIGH
Service accounts | Backend | Non-human accounts for CI/CD with scoped permissions | backend/src/services/service-accounts.ts | 3h | HIGH
IP allowlisting | Backend | Restrict API access to specific IP ranges per org | backend/src/middleware/ip-allowlist.ts | 2h | MEDIUM
Day 5 - Fri Jun 6
Task | Area | Description | File/Location | Est. | Priority
SOC2 preparation | DevOps | Security controls documentation, access reviews, encryption audit | compliance/soc2/ | 4h | HIGH
Data encryption at rest | Backend | AES-256 encryption for stored test data, screenshots, credentials | backend/src/services/encryption.ts | 3h | HIGH
Vulnerability scanning CI | DevOps | Snyk/Trivy in CI pipeline for dependency vulnerabilities | .github/workflows/security.yml | 1h | MEDIUM
Day 6-7 - Sat-Sun Jun 7-8
Task | Area | Description | File/Location | Est. | Priority
Custom branding (white-label) | Frontend | Enterprise customers can set logo, colors, domain | frontend/src/pages/admin/Branding.tsx | 3h | MEDIUM
Custom domain support | DevOps | Enterprise: tests.company.com pointing to Qestro | backend/src/services/custom-domain.ts | 3h | MEDIUM
Enterprise onboarding flow | Frontend | Guided setup: SSO → team → permissions → first project | frontend/src/pages/EnterpriseOnboarding.tsx | 2h | HIGH
Unit tests for enterprise features | Testing | RBAC, SAML, audit tests with 85% coverage | tests/enterprise/ | 2h | HIGH
Day 8 - Mon Jun 9
Task | Area | Description | File/Location | Est. | Priority
Scheduled test runs v2 | Backend | Cron-based scheduling with timezone support, parallel sharding | backend/src/services/TestSchedulerService.ts | 3h | HIGH
Schedule UI (calendar view) | Frontend | Visual calendar of scheduled test runs across projects | frontend/src/pages/Schedule.tsx | 3h | HIGH
Maintenance windows | Backend | Pause tests during deployments, auto-resume after | backend/src/services/maintenance.ts | 2h | MEDIUM
Day 9 - Tue Jun 10
Task | Area | Description | File/Location | Est. | Priority
Jira integration (real) | Backend | Create Jira tickets from failed tests, sync status | backend/src/services/jira.ts | 3h | HIGH
Linear integration | Backend | Create Linear issues from failures, bi-directional sync | backend/src/services/linear.ts | 3h | MEDIUM
Test-to-ticket linking | Frontend | View linked tickets on test results, auto-close on pass | frontend/src/components/TicketLink.tsx | 2h | MEDIUM
Day 10 - Wed Jun 11
Task | Area | Description | File/Location | Est. | Priority
Multi-environment management | Backend | Run same tests across dev, staging, prod environments | backend/src/services/environments.ts | 3h | HIGH
Environment comparison view | Frontend | Side-by-side: this test passes on staging, fails on prod | frontend/src/pages/EnvCompare.tsx | 3h | MEDIUM
Secret management (Vault) | Backend | Store test credentials securely, inject at runtime | backend/src/services/secrets.ts | 2h | HIGH
Day 11 - Thu Jun 12
Task | Area | Description | File/Location | Est. | Priority
Enterprise sales page | Frontend | Enterprise landing: ROI, compliance, case studies, contact form | frontend/src/pages/Enterprise.tsx | 3h | HIGH
Admin dashboard | Frontend | Internal: user growth, revenue, usage, health metrics | frontend/src/pages/admin/Dashboard.tsx | 3h | HIGH
Customer success dashboard | Frontend | Per-customer health: usage, feature adoption, risk signals | frontend/src/pages/admin/CustomerHealth.tsx | 2h | MEDIUM
Day 12 - Fri Jun 13
Task | Area | Description | File/Location | Est. | Priority
Enterprise pilot outreach | Sales | Identify 10 target companies, craft personalized outreach | marketing/enterprise/ | 4h | CRITICAL
Enterprise demo script | Sales | 30-min enterprise demo: SSO → team setup → test gen → CI → reports | marketing/enterprise/demo-script.md | 2h | HIGH
Pricing page v2 (enterprise tier) | Frontend | Add enterprise tier with custom pricing, contact sales CTA | frontend/src/pages/Pricing.tsx | 2h | HIGH
Day 13-14 - Sat-Sun Jun 14-15
Task | Area | Description | File/Location | Est. | Priority
Full security audit | Testing | Penetration testing, auth bypass attempts, data isolation | tests/security/ | 4h | CRITICAL
Enterprise E2E test suite | Testing | SSO login → team create → RBAC → audit → scheduled run | tests/enterprise-e2e/ | 3h | HIGH
Sprint 5 retrospective | All | Enterprise readiness review, SOC2 gap analysis | Various | 1h | HIGH
Enterprise pilot kickoff | Sales | Start first enterprise pilot with target company | Various | 2h | CRITICAL
SPRINT TOTALS: 38 tasks ¦ 7 CRITICAL ¦ 21 HIGH ¦ 10 MEDIUM/LOW

## Sprint 6 — Domination
SPRINT 6 — DOMINATION
June 16-29, 2026
GOAL: Plugin marketplace, load testing, desktop agent, GA launch. Establish Qestro as THE testing platform for AI-era developers.
Day 1 - Mon Jun 16
Task | Area | Description | File/Location | Est. | Priority
Plugin system architecture | Backend | Plugin API: register, install, configure, execute custom runners | backend/src/services/plugin-system.ts | 4h | CRITICAL
Plugin SDK | Backend | npm package: @qestro/plugin-sdk with types, helpers, examples | packages/plugin-sdk/ | 3h | HIGH
Plugin marketplace UI | Frontend | Browse, install, rate, review community plugins | frontend/src/pages/Marketplace.tsx | 1h | HIGH
Day 2 - Tue Jun 17
Task | Area | Description | File/Location | Est. | Priority
Built-in plugins: Lighthouse | Backend | Performance audit plugin using Google Lighthouse | plugins/lighthouse/ | 3h | HIGH
Built-in plugins: Storybook | Backend | Auto-test Storybook components via Qestro | plugins/storybook/ | 2h | MEDIUM
Built-in plugins: Figma diff | Backend | Compare implementation vs Figma design, flag deviations | plugins/figma-diff/ | 3h | HIGH
Day 3 - Wed Jun 18
Task | Area | Description | File/Location | Est. | Priority
Load testing module | Backend | k6 integration: run tests under load, measure breaking points | orchestrator/src/runners/load-runner.ts | 4h | HIGH
Load test configuration UI | Frontend | Configure: users, ramp-up, duration, thresholds | frontend/src/pages/LoadTesting.tsx | 3h | HIGH
Load test results visualization | Frontend | Real-time charts: RPS, latency, error rate, throughput | frontend/src/components/LoadChart.tsx | 1h | MEDIUM
Day 4 - Thu Jun 19
Task | Area | Description | File/Location | Est. | Priority
Desktop agent (Electron) | Frontend | Local desktop app: run tests locally, sync to cloud | desktop/src/ | 4h | MEDIUM
Local test execution | Desktop | Execute Playwright locally without cloud, faster feedback | desktop/src/local-runner.ts | 3h | MEDIUM
Desktop ↔ cloud sync | Desktop | Sync test results, configs between desktop and cloud | desktop/src/sync.ts | 1h | MEDIUM
Day 5 - Fri Jun 20
Task | Area | Description | File/Location | Est. | Priority
AI test maintenance agent | AI/Backend | Background agent: monitor test health, auto-heal, alert | orchestrator/src/agents/maintenance.ts | 4h | HIGH
Smart test selection (AI) | AI/Backend | Given code diff, select minimum tests to verify change | orchestrator/src/agents/smart-select.ts | 3h | HIGH
Impact analysis | AI/Backend | Code change → predict which tests will be affected | orchestrator/src/agents/impact-analyzer.ts | 1h | MEDIUM
Day 6-7 - Sat-Sun Jun 21-22
Task | Area | Description | File/Location | Est. | Priority
Multi-language support (i18n) | Frontend | English, Spanish, Portuguese, Japanese, German | frontend/src/i18n/ | 3h | MEDIUM
Dark/light theme polish | Frontend | Pixel-perfect dark and light themes across all pages | frontend/src/styles/ | 2h | MEDIUM
Accessibility audit (WCAG AA) | Frontend | Ensure Qestro itself passes WCAG 2.1 AA | tests/a11y/ | 2h | MEDIUM
Mobile responsive polish | Frontend | Dashboard usable on tablet and mobile | frontend/src/styles/ | 3h | MEDIUM
Day 8 - Mon Jun 23
Task | Area | Description | File/Location | Est. | Priority
Open-source repo polish | All | README, CONTRIBUTING, LICENSE, examples, GitHub topics | Various | 3h | HIGH
Community plugin contest | Marketing | Launch: build a Qestro plugin, win prizes + recognition | marketing/community/ | 2h | HIGH
Developer advocacy content | Marketing | Technical blog posts, conference talk proposals, podcasts | marketing/advocacy/ | 3h | MEDIUM
Day 9 - Tue Jun 24
Task | Area | Description | File/Location | Est. | Priority
GA launch marketing blitz | Marketing | Press release, email blast, partner announcements | marketing/ga-launch/ | 4h | CRITICAL
Partner integrations page | Frontend | Showcase: GitHub, GitLab, Jira, Slack, VS Code, Cursor | frontend/src/pages/Integrations.tsx | 2h | HIGH
Customer testimonials | Marketing | Collect and display beta user testimonials with metrics | marketing/testimonials/ | 2h | HIGH
Day 10 - Wed Jun 25
Task | Area | Description | File/Location | Est. | Priority
GENERAL AVAILABILITY LAUNCH | All | Production launch: app.qestro.io, all features enabled | Various | 8h | CRITICAL
Day 11 - Thu Jun 26
Task | Area | Description | File/Location | Est. | Priority
Post-launch monitoring | DevOps | 24h war room: monitor errors, performance, user feedback | Various | 4h | CRITICAL
Launch-day bug hotfixes | All | Immediate fixes for any P0/P1 issues | Various | 4h | CRITICAL
Day 12 - Fri Jun 27
Task | Area | Description | File/Location | Est. | Priority
User analytics review | Product | Analyze launch metrics: signups, activation, test gen usage | Various | 3h | HIGH
Conversion funnel optimization | Frontend | Fix drop-off points in signup → first test → upgrade funnel | frontend/src/ | 3h | HIGH
Enterprise follow-ups | Sales | Follow up with enterprise pilot customers, close deals | Various | 2h | CRITICAL
Day 13-14 - Sat-Sun Jun 28-29
Task | Area | Description | File/Location | Est. | Priority
Comprehensive regression suite | Testing | Full platform regression: every feature, every browser, mobile | tests/ | 4h | HIGH
Performance baseline (GA) | Testing | Document GA performance: response times, throughput, uptime | tests/performance/ | 2h | HIGH
SPRINT 6 RETROSPECTIVE | All | Full 6-sprint retrospective, Q3 planning, celebrate! | Various | 2h | HIGH
Q3 roadmap planning | Product | Plan next quarter: AI agents, enterprise expansion, global scale | docs/roadmap-q3.md | 2h | HIGH
SPRINT TOTALS: 35 tasks ¦ 6 CRITICAL ¦ 18 HIGH ¦ 11 MEDIUM/LOW

## Competitor Warfare
COMPETITOR WARFARE MAP
Know your enemy. Beat them on every dimension.
Feature | Qestro | TestMu AI | Momentic | QA Wolf | Cypress | Playwright
Vibe Test Pilot (URL→tests) | YES | No | Partial | No | No | No
MCP Server (AI IDE native) | YES | No | No | No | No | Yes (community)
Self-Healing Tests | YES | Yes | Yes | Yes | No | No
Visual Regression | YES | Yes (Smartui) | No | No | No | No
Browser Testing | YES | Yes | Yes | Yes | Yes | Yes
Mobile Testing (native) | YES | Yes | No | No | No | Partial
API Testing | YES | Yes | No | Yes | No | Yes
Open-Source CLI | YES | No | No | No | Yes | Yes
AI Test Generation | YES | Yes | Yes | Partial | No | No
GitHub Action (1-line) | YES | Yes | No | No | Yes | Yes
Natural Language Tests | YES | Yes | Yes | No | No | No
Load Testing | YES | No | No | No | No | No
Qestro Score Badge | YES | No | No | No | No | No
Plugin Marketplace | YES | No | No | No | Yes | No
Desktop Agent | YES | No | No | No | Yes | No
Unified Platform | YES | Partial | No | No | No | No
Free Tier | YES | Yes | No | No | Yes | Yes
Pricing | From $0 | $108+/mo | Custom | Service | $0-$500 | Free
Funding | Bootstrap | $108M | $15M | $56M | Acquired | Microsoft
HOW QESTRO BEATS EACH COMPETITOR
vs TestMu AI ($108M funded) |  | They're enterprise-heavy, expensive, and bloated. Qestro is fast, developer-first, open-source core. We win on DX, price, and vibe coding focus. Their MCP gap is our entry point.
vs Momentic ($15M YC) |  | They do AI test gen but no mobile, no API, no open-source. We offer the unified platform they can't. Plus our MCP server works in Cursor where their devs already code.
vs QA Wolf ($56M) |  | QA Wolf is a SERVICE, not a product. $56M to pay humans to write tests. Qestro replaces their entire business model with AI. We're 10x cheaper and infinitely scalable.
vs Cypress (acquired) |  | Cypress is last generation — no AI, no mobile, no API. But they have the community. We take their open-source playbook and add AI. The Qestro CLI IS the next Cypress.
vs Playwright (Microsoft) |  | Playwright is a framework, not a platform. We BUILD ON Playwright and add everything it lacks: AI generation, self-healing, dashboards, mobile, CI. We're Playwright++.

## Testing Matrix
FULL TESTING MATRIX — NO SHORTCUTS
Every feature. Every browser. Every device. Every persona. Full coverage.
Authentication & Security
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Email/password registration | E2E | Chrome, Firefox, Safari | Jest + PW | Sprint 1 | CRITICAL
Email verification flow | E2E | Chrome | PW | Sprint 1 | CRITICAL
Login/logout | E2E | Chrome, Firefox, Safari, Edge | PW | Sprint 1 | CRITICAL
Google OAuth SSO | Integration | Chrome, Firefox | PW + Mock | Sprint 1 | HIGH
GitHub OAuth SSO | Integration | Chrome, Firefox | PW + Mock | Sprint 1 | HIGH
SAML SSO (Azure AD) | Integration | Chrome | PW + SAML Mock | Sprint 5 | CRITICAL
SAML SSO (Okta) | Integration | Chrome | PW + SAML Mock | Sprint 5 | CRITICAL
JWT refresh token rotation | Unit | N/A | Jest | Sprint 1 | CRITICAL
Password reset flow | E2E | Chrome, Firefox | PW | Sprint 1 | HIGH
Rate limiting (brute force) | Integration | N/A | Jest + Supertest | Sprint 1 | HIGH
RBAC permission checks | Unit + E2E | Chrome | Jest + PW | Sprint 5 | CRITICAL
API key auth | Integration | N/A | Jest + Supertest | Sprint 5 | HIGH
Test Creation & Editing
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Create test case (manual) | E2E | Chrome, Firefox, Safari | PW | Sprint 1 | HIGH
Vibe Test Pilot (URL → tests) | E2E | Chrome | PW | Sprint 2 | CRITICAL
Natural language test refinement | E2E | Chrome | PW | Sprint 2 | HIGH
Test code editor (Monaco) | E2E | Chrome, Firefox | PW | Sprint 2 | HIGH
API test builder | E2E | Chrome | PW | Sprint 3 | HIGH
Browser recording → test code | E2E | Chrome | PW | Sprint 3 | HIGH
Test tagging and filtering | E2E | Chrome | PW | Sprint 3 | MEDIUM
Bulk operations (multi-select) | E2E | Chrome | PW | Sprint 3 | MEDIUM
Template gallery (fork) | E2E | Chrome | PW | Sprint 4 | MEDIUM
Test Execution
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Playwright execution (Chrome) | Integration | Chrome | PW | Sprint 1 | CRITICAL
Playwright execution (Firefox) | Integration | Firefox | PW | Sprint 3 | HIGH
Playwright execution (Safari) | Integration | Safari | PW | Sprint 3 | HIGH
Cross-browser matrix (parallel) | Integration | All | PW | Sprint 3 | HIGH
Mobile: Maestro iOS | Integration | iOS Sim | Maestro | Sprint 3 | CRITICAL
Mobile: Maestro Android | Integration | Android Sim | Maestro | Sprint 3 | CRITICAL
API test execution | Integration | N/A | Jest | Sprint 2 | HIGH
Scheduled test runs (cron) | Integration | N/A | Jest | Sprint 5 | HIGH
Parallel sharding | Integration | N/A | Jest | Sprint 3 | HIGH
Load testing (k6) | Integration | N/A | k6 | Sprint 6 | MEDIUM
Self-Healing & AI
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Selector healing (DOM change) | Unit + Integration | Chrome | Jest + PW | Sprint 3 | CRITICAL
Timing healing (flaky waits) | Unit | N/A | Jest | Sprint 3 | HIGH
API schema healing | Unit | N/A | Jest | Sprint 3 | HIGH
Visual regression detection | Integration | Chrome | PW + Pixelmatch | Sprint 3 | CRITICAL
Auto-retry with healing | Integration | Chrome | PW | Sprint 3 | HIGH
Smart test selection (AI) | Unit | N/A | Jest | Sprint 6 | MEDIUM
Impact analysis | Unit | N/A | Jest | Sprint 6 | MEDIUM
Dashboard & Analytics
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Dashboard stats (real data) | E2E | Chrome, Firefox | PW | Sprint 1 | HIGH
Test results viewer | E2E | Chrome | PW | Sprint 1 | HIGH
Analytics trends chart | E2E | Chrome | PW | Sprint 3 | HIGH
Flakiness heatmap | E2E | Chrome | PW | Sprint 3 | MEDIUM
Export reports (PDF/JUnit/CSV) | Integration | N/A | Jest | Sprint 3 | HIGH
Qestro Score display | E2E | Chrome | PW | Sprint 2 | HIGH
Integrations
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
GitHub App (PR comments) | Integration | N/A | Jest + Mock | Sprint 2 | HIGH
GitHub Action | Integration | N/A | GH Actions | Sprint 4 | CRITICAL
GitLab CI template | Integration | N/A | GitLab | Sprint 4 | HIGH
Jira ticket creation | Integration | N/A | Jest + Mock | Sprint 5 | HIGH
Slack notifications | Integration | N/A | Jest + Mock | Sprint 3 | HIGH
Stripe billing | Integration | N/A | Jest + Stripe Mock | Sprint 1 | HIGH
MCP server tools | Integration | N/A | Jest | Sprint 2 | CRITICAL
VS Code extension | E2E | VS Code | PW | Sprint 4 | HIGH
Personas
Test Case | Type | Browsers/Env | Framework | Sprint | Priority
Solo Dev: signup → first test → run | E2E | Chrome | PW | Sprint 2 | CRITICAL
Solo Dev: URL → AI test suite → badge | E2E | Chrome | PW | Sprint 2 | CRITICAL
Team Lead: invite team → assign tests | E2E | Chrome | PW | Sprint 5 | HIGH
QA Engineer: mobile matrix → reports | E2E | Chrome | PW | Sprint 3 | HIGH
Enterprise: SSO → RBAC → audit → schedule | E2E | Chrome | PW | Sprint 5 | CRITICAL
Vibe Coder: paste URL → chat refine → PR comment | E2E | Chrome | PW | Sprint 2 | CRITICAL
TOTAL TEST CASES: 58 ¦ Target Coverage: 85%+ ¦ Zero flaky tests tolerance